## Sheet1
CMPT 371 Team 3 - Activity Log
| Name: | Kevin Noonan
| Position: | Developer
|  | Date | Activity | Estimated Time (hrs) | Actual Time (hrs)
|  | 2017-01-09 | Meeting ¦ Met with the team, introductions | 1 | 1
|  | 2017-01-10 | Meeting ¦ Go over roles, decide the project | 1.5 | 1.5
|  | 2017-01-12 | Meeting ¦ Solidify project choice | 0.5 | 0.5
|  | 2017-01-14 | Meeting ¦ Meet with the client | 1 | 1
|  | 2017-01-17 | Inspection ¦Code of Conduct | 1 | 1
|  | 2017-01-23 | Meeting ¦ Discuss infrastructure, presentation | 1.5 | 1.25
|  | 2017-01-25 | Meeting ¦ Development team | 1 | 1
|  | 2017-01-26 | Switch to Developer from Tester | 0 | 0
|  | 2017-01-28 | Work on Developing Environment for VR in Unity | 4 | 4
|  | 2017-01-29 | Tour of the Radiology centre | 1 | 1
|  | 2017-01-31 | Attempt to set up VR and Test Environment | 2.5 | 2.5
|  | 2017-01-31 | Inspection ¦ Risk Inspection | 1.5 | 1.5
|  | 2017-02-01 | Pair Program with Silvia | 3 | 3
|  | 2017-02-03 | Attempt to test VR | 1 | 1
|  | 2017-02-04 | Development Session | 7 | 7.5
|  | 2017-02-05 | Research into Touch Controls and Gestures | 2 | 2
|  | 2017-02-08 | Meeting ¦ Development team | 1 | 1
ID 1 | Subtotals |  |  | 30.5 | 30.75 | Comments for ID:
|  | 2017-02-09 | Development Session + Home coding | 10 | 10
|  | 2017-02-10 | Development Session + Home coding | 8 | 8
|  | 2017-02-11 | Development Session + Home coding | 6 | 6
|  | 2017-02-12 | Development Session ¦ Meeting with Client | 3 | 3
|  | 2017-02-15 | Final Development for ID2 implementing the finished scene | 2 | 4
ID2 | Subtotals |  |  | 29 | 31 | Comments for ID:
ID3 | Subtotals |  |  | 0 | 0 | Comments for ID:
ID4 | Subtotals |  |  | 0 | 0 | Comments for ID:
ID5 | Subtotals |  |  | 0 | 0 | Comments for ID:
Project totals |  |  |  | 32 | 34 | Comments for Project: