## Sheet1
Man-hours since beginning of ID3
ID | Thing | Predecessors | Best | Worst | Expected | Actual | Difference | Estimate breakdown
A | Integrate DICOM library |  | 5 | 10 | 7 | 19 | 12 | 1 person, download and test library in environment
B | Filesystem Interface |  | 60 | 120 | 90 | ((40)) |  | 4 devs x 15 hours each (5 x 3 hour sessions), 3 testers x 10 hours each
C | DICOM information parsed, visible in program | A | 25 | 60 | 32 |  |  | 2 devs x ~12 hours each (matching format, creating display for information, research), 1 tester x 7 hours
D | Motion sickness report |  | 15 | 20 | 18 | 13.5 | -4.5 | Dev Lead 15 hours, dev 5 hours
E | Identify, design anti-sickness features | D | 5 | 15 | 8 |  |  | 1 hour meeting x ~6 people, 2 hours design by Dev Lead/Triage Lead
F | Implement anti-sickness features | E | 80 | 200 | 120 |  |  | High estimate for safety; depends on how many/which features are implemented
G | Copy modification (brightness, zoom etc.) |  | 35 | 70 | 55 | ((52)) |  | 4 devs x 10 hours each, 3 testers x 5 hours each
H | Grid for Copies | G | 40 | 125 | 75 |  |  | 3 devs x 20 hours each, 2 testers x ~8 hours each
I | User-facing UI | B | 8 | 30 | 12 | 14 | 2 | 1 dev x 10 hours, 1 tester x 2 hours
J | Initial round of formal user testing | G, I | 7 | 20 | 10 | 13.5 | 3.5 | PM and Lead Tester x 1 hours prep, 3 people (1 dev + 1 tester + PM) x 2 hour testing session, 2 hours formal report creation
K | Report dictation |  | 25 | 80 | 40 |  |  | 2 devs x 15 hours, 2 testers x 5 hours
L | Save/load reports | K | 15 | 55 | 30 |  |  | 2 devs x 10 hours, 1 tester x 10 hours
M | Showcase-ready prototype | J | 10 | 20 | 14 | 16 | 2 | PM x 4 hours, 2 devs x 3 hours, 1 tester x 4 hours
N | SIIM Application | M | 140 | 220 | 180 | 80 + 103 | 3 | ~3 people x 60 real-time hours (application 20, video 40)
O | Stress test | R | 10 | 30 | 15 |  |  | 5 hours prep, 4 people x 2 hours test, 2 hours formal report/debrief
P | Refined UI | M | 20 | 100 | 60 |  |  | 5 devs x 10 hours, 2 testers x 5 hours
Q | Mid ID5 Build | B, C, P, Y | 10 | 25 | 15 |  |  | 3 people x 5 hours
R | Test with Radiologists | Q | 8 | 15 | 10 |  |  | 3 people x 2 hours, 1 hour report, 1 hour setup, 2 hours communication
S | Reduce Latency | E | 30 | 50 | 40 |  |  | 3 devs x 10 hours, 2 testers x 5 hours
T | ID5 Build | H, O, S | 10 | 20 | 15 |  |  | 3 people x 5 hours
U | Defect fixes and documentation | T | 30 | 50 | 40 |  |  | 4 people x 10 hours
V | User Documentation |  | 20 | 60 | 35 |  |  | 5 people x 1 hour meeting, 2 people x 10 hours, 10 people x 1 hour inspection
W | Programmer Documentation |  | 30 | 70 | 50 |  |  | 4 people x 12 hours, 2 hours proofreading
X | ID5 Submission | U, V, W | 10 | 25 | 17 |  |  | 3 people x 5 hours + PM extra 2 hours
Y | 3D Volume Scans Load |  | 15 | 45 | 30 |  |  | 2 people x 10 hours, 2 testers x 5 hours