## Sheet1
Date | Mini-Milestone | Passed? | Comments
2017-01-22 | Requirements Doc First Draft | YES
2017-01-26 | Risk Assessment First Draft | YES
2017-01-31 | Architecture and Design Specs First Draft | YES
2017-02-01 | VR app builds with generic environment, interaction | NO | Team did not receive access to VR hardware until 02/02/17
2017-02-03 | Testing Plan First Draft | YES
2017-02-05 | ID 1 Ends
2017-02-10 | Prototype functionality rebuilt with proper practices, unit tests | NO | Partially rebuilt, difficulties implementing unit tests
2017-02-11 | Moving, resizing, opening and closing monitors in application | NO | Only moving monitors implemented
2017-02-13 | DICOM library integrated into application, a test image loads with metadata | NO | Further discussion with Luxsonic required
2017-02-14 | 5+ Defects Logged | NO
2017-02-15 | Touch controllers integrated into project | YES | Integrated by 2/12/17, presented at client meeting
2017-02-17 | ID 2 Ends
2017-02-25 | Cycle through depths/time series of DICOM images
2017-02-28 | Bug party completed
ID 3 Ends
2017-03-12 | Load and display a 3D volumetric scan in the application
2017-03-16 | 3+ medical professionals have demoed the software
ID 4 Ends
2017-03-27 | Held a stress test for the application
2017-03-30 | User documentation rough draft completed
ID 5 Ends