## Sheet1
CMPT 371 Team 3 - Activity Log
| Name: | Mackenzie Power
| Position: | Lead Dev
Tuesday/Thursday In-class hours NOT included
|  | Date | Activity | Estimated Time (hrs) | Actual Time (hrs)
|  | Before Jan 27th | Worked on Requirements document, Meetings, DICOM research, etc. | 35 | 35 | This Value is unknown, Complete Guess
|  | Jan 28th | Requirements Critique Meeting, Fixed Sequence diagram, continued work on the design document | NA | 8
|  | Jan 29th | Work on design document, finish design document, Luxsonic meeting, | 6 | 8.5
|  | Jan 30th | Resume DICOM report, DICOM research, set project for pair programing, write-up roles and tasks and pairs |  | 3.5
|  | Jan 31st | Attempted Oculus Rift set up with Kevin (we failed) | 1 | 2.5
|  |  | Continued DICOM research | 3 | 3
|  | Feb 1st | Continued DICOM research | 5 | 5
|  |  | Integrated File retreival in Unity | 1 | 3
|  | Feb 2nd | Finished and worte up initial draft of DICOM report | 1 | 2
|  |  | More DICOM research | 5 | 5
|  |  | Looking for ways to decipher uploaded DICOMs in Unity (basically research) | 1 | 3
|  | Feb 3rd | Continued DICOM research | 2 | 4
|  |  | Searching for and trying out ways to Decipher DICOMs in Unity | 2 | 5
|  | Feb 4th | Work on DICOM report and integration with rest of the Dev team on incorporating sections together |  | 6
|  | Feb 5th | Work on merging branch with 'development' | 0.5 | 0.5
ID 1 | Subtotals |  |  | 62.5 | 94 |  | Comments for ID:
|  | Feb 6th | Meeting for ID1 Presentation and Debreif | 1 | 1
|  |  | Write up slide info and determine what to say | 0.5 | 0.5
|  | Feb 7th | Write up Checklist for Developers to complete | 1 | 1
|  |  | Practise for Presentation | 1.5 | 1.5
|  |  | Presentation | 0.3 | 0.3
|  | Feb 8th | Tester meeting | 1 | 1
|  |  | Developer Meeting | 1 | 1
|  |  | Updated Design/Requirements document, added classes and changed UML | 3 | 3
|  |  | Create ID2_Load branch and begin implementation | 1 | 1
|  | Feb 9th | Work on Load implementation | 4 | 9.5
|  | Feb 10th | Due to yesterdays failure, will work on implementing a File Browser | 5 | 5
|  |  | Create Nunit test for the LoadBar class, Work with Evan doing Nunit implementation | 1.5 | 3
|  | Feb 11th | More Unit test work | 1 | 1
|  |  | Merging branches | 0.5 | 0.5
|  |  | Integrate all scripts and objects into a working scene | 4 | 6.5
|  | Feb 12th | Built Infastructure for new File Browser | 3 | 3
|  |  | Demo with Mike | 1 | 1
|  | Feb 13th | NA | 0 | 0
|  | Feb 14th | Lab meeting | 1.5 | 1.75
|  | Feb 15th | Disscuss new Design specifications with Dev | 1.5 | 2
|  |  | Determine Unit Test Problem | 1 | 1
|  |  | Integrate Features into a workable format for ID2 | 2 | 2
|  |  | Fix my Unit test failures | 1 | 2.5
Feb 16th
Feb 17th
ID2 | Subtotals |  |  | 37.3 | 49.05 |  | Comments for ID:
ID3 | Subtotals |  |  | 0 | 0 |  | Comments for ID:
ID4 | Subtotals |  |  | 0 | 0 |  | Comments for ID:
ID5 | Subtotals |  |  | 0 | 0 |  | Comments for ID:
Project totals |  |  |  | 99.8 | 143.05 |  | Comments for Project: