## Sheet1
Date | Mini-Milestone | On time? | Completed by end of ID? | Comments
2017-01-22 | Requirements Doc First Draft | YES | YES
2017-01-26 | Risk Assessment First Draft | YES | YES
2017-01-31 | Architecture and Design Specs First Draft | YES | YES
2017-02-01 | VR app builds with generic environment, interaction | NO | YES | Team did not receive access to VR hardware until 02/02/17
2017-02-03 | Testing Plan First Draft | YES | YES
2017-02-05 | ID 1 Ends
2017-02-10 | Prototype functionality rebuilt with proper practices, unit tests | NO | YES | Partially rebuilt, difficulties implementing unit tests
2017-02-11 | Moving, resizing, opening and closing monitors in application | NO | NO | Only moving monitors implemented
2017-02-13 | DICOM library integrated into application, a test image loads with metadata | NO | NO | Further discussion with Luxsonic required
2017-02-14 | 5+ Defects Logged | NO | YES | Team required discussion on which defects are appropriate to log and when
2017-02-15 | Touch controllers integrated into project | YES | YES | Integrated by 2/12/17, presented at client meeting
2017-02-17 | ID 2 Ends
2017-02-22 | Image-viewing room has a ceiling, no skybox visible | NO | NO | Will be implemented when VR distance has been more formally calculated, to prevent objects clipping into the ceiling.
2017-02-26 | File system interface implemented | NO | NO | Exists in prototype form only
2017-02-25 | DICOM Library integrated into system | YES | YES | Fellow Oak DICOM library was selected for the project and crude tests pass
2017-02-27 | Risk Scan for ID3 completed | NO | YES
2017-02-27 | Anti-motion-sickness report completed | NO | YES
2017-02-28 | 40+ defects logged | NO | YES
2017-02-28 | Dashboard and Tray implemented | YES | YES
2017-03-01 | 3+ system tests implemented into project | NO | YES | Tests are implemented but still need development work to pass.
2017-03-01 | Quit button, other user-facing UI implemented | NO | YES
2017-03-02 | At least one image modification available for Copy objects | NO | YES | The Brightness slider was implemented, but may need some rework in a later sprint.
2017-03-04 | 2+ user testing sessions completed (eg. users with glasses and no glasses) | NO | NO | Developers and testers agreed the build needed more work before formal user testing would be productive.
2017-03-05 | ID 3 Ends
2017-03-12 | "Showcase" build completed (focus on UI, user experience, aesthetics) | YES | YES
2017-03-16 | Snap-to-grid for copies implemented | NO | NO | Shifted to the next incremental deliverable
2017-03-17 | 1+ bug party completed | NO | YES | Completed on March 18
2017-03-18 | 5+ user testing sessions completed | YES | YES | Completed on March 16
2017-03-18 | 75+ defects logged | YES | YES | The bug party was a great success!
2017-03-19 | Test plan overhauled to focus on manual testing | YES | YES
2017-03-19 | ID 4 Ends
2017-03-24 | 10+ user testing sessions completed | YES | YES | 2 radiologists and 11 regular users by this date.
2017-03-26 | DICOM and File Browser integrated | YES | YES | Completed on March 25, latency reduced on March 26
2017-03-29 | DICOM Report Window completed
2017-03-30 | 3D volume scan successfully loaded into application
2017-03-30 | Held a stress test for the application
2017-03-30 | 3+ medical professionals have demoed the software
2017-03-30 | User documentation first draft completed
2017-04-02 | 2+ bug parties completed
2017-04-05 | Programmer documentation first draft completed
2017-04-05 | Remaining defects documented
2017-04-05 | User documentation final draft completed
2017-04-06 | ID 5 Ends