## Sheet1
CMPT 371 Team 3 - Activity Log
| Name: | Janelle Hindman
| Position: | Project Manager
|  | Date | Activity | Estimated Time (hrs) | Actual Time (hrs)
|  | 2017-01-15 | Meetings for the week | 3 | 4
|  | 2017-01-16 | Creating master schedule, requirements change policy, code of conduct, other project manager documents | 4 | 7
|  | 2017-01-19 | Proofread and handle Hardware/Software Recommendation doc | 0.5 | 1
|  | 2017-01-21 | Client correspondence for the week | 1 | 1.5
|  | 2017-01-21 | Department correspondence for the week | 1 | 1
|  | 2017-01-21 | Meetings for the week | 5 | 5
|  | 2017-01-27 | Updating wiki, task list, documents in repository | 1 | 2
|  | 2017-01-28 | Client correspondence for the week | 1 | 1
|  | 2017-01-28 | Meetings for the week | 3 | 3
|  | 2017-02-02 | Oculus Rift hardware setup and group tutorial | 2 | 2
|  | 2017-02-03 | DICOM library research | 1 | 1
|  | 2017-02-04 | Proofreading and collecting documents for ID1 | 2 | 3
|  | 2017-02-04 | Meetings for the week | 2 | 2
|  | 2017-02-05 | Collecting documents for ID1 | 3 | 5
ID 1 | Subtotals |  |  | 26.5 | 34.5 | Comments for ID: | Client correspondence can turn into a bottleneck. Must anticipate possible delays while waiting for replies from the client. Proofreading will always take more time than you expect.
|  | 2017-02-06 | ID 1 debriefing | 1 | 1
|  | 2017-02-07 | Presentation preparation, correspondence, proofreading | 1 | 1
ID2 | Subtotals |  |  | 2 | 2 | Comments for ID:
ID3 | Subtotals |  |  | 0 | 0 | Comments for ID:
ID4 | Subtotals |  |  | 0 | 0 | Comments for ID:
ID5 | Subtotals |  |  | 0 | 0 | Comments for ID:
Project totals |  |  |  | 28.5 | 36.5 | Comments for Project: